## Sheet1
ID | Task Name | Phase | Dependency | Duration (days)
1 | 1.1 Approve Project Charter | Initiation
2 | 1.2 Identify stakeholders and recruitment target audience | Initiation
3 | 1.3 Confirm hosting environment (Hostinger) and domain/subdomain strategy | Initiation
4 | 2.1 Finalize Project Scope Statement | Planning | 1
5 | 2.2 Define database schema and migration plan | Planning
6 | 2.3 Define CORS policy for LAN and production | Planning
7 | 2.4 Plan integration into andrewholland.com header and monk.andrewholland.com | Planning
8 | 3.1 Consolidate to FastAPI backend (/api/chat) | Execution | 5
9 | 3.2 Standardize environment variables (GOOGLE_API_KEY) | Execution | 8
10 | 3.3 Update frontend (index.html, script.js) to point to FastAPI | Execution | 8
11 | 3.4 Align monitoring.py to unified schema with timestamp | Execution | 5
12 | 3.5 Implement logging and health checks | Execution | 8
13 | 3.6 Test backend with LAN and curl | Execution | 8
14 | 3.7 Deploy LAN version | Execution | 13
15 | 3.8 Deploy production version on Hostinger | Execution | 14
16 | 4.1 Validate chatbot response times and recruiter flow | Monitoring & Controlling | 15
17 | 4.2 Monitor API usage and Gemini quota | Monitoring & Controlling | 15
18 | 4.3 Check database caching and retrieval | Monitoring & Controlling | 15
19 | 4.4 Review logs for errors and warnings | Monitoring & Controlling | 15
20 | 4.5 Verify CORS compliance and security settings | Monitoring & Controlling | 15
21 | 5.1 Archive legacy Flask backend | Closing | 15
22 | 5.2 Finalize deployment documentation | Closing | 21
23 | 5.3 Deliver final recruiter experience review | Closing | 22
24 | 5.4 Project closure and sign-off | Closing | 23